## TEAM RAIDLOG
MDY MART TEAM AGILE RAIDLOG
RISKS
No. | Task | Mitigation/Action Plan | Start Date | End Date | Duration in days | RAID Category | Impact | Probability | Status | Owner
1 | Limited stakeholder availability during workshops and UAT. | Secure time commitments from functional heads; communicate schedules early; escalate non-attendance. |  |  |  | Risk | Moderate | High | Open | Project Manager
2 | Delay in data migration due to incomplete or poor-quality legacy data. | Conduct early data profiling and cleansing; assign data owners; establish a migration mock schedule. |  |  |  | Risk | High | High | Open | Data & System Admin Lead
3 | Unstable internet or infrastructure affecting remote sessions and cloud access. | Plan backup connectivity options; coordinate with IT to monitor system health. |  |  |  | Risk | High | Moderate | Open | IT / Infra Lead
4 | Scope creep due to unapproved local requirements. | Enforce strict change control via PMO; maintain approved backlog. |  |  |  | Risk | High | Moderate | Open | PMO / Project Manager
5 | Delays in integration setup between SAGE Cloud and external systems (banks, POS, etc.). | Early identification of interface dependencies; allocate integration sprints. |  |  |  | Risk | High | Moderate | Open | Technical Integration Lead
6 | Insufficient user adoption post go-live. | Deliver comprehensive training, communication, and post-go-live handholding. |  |  |  | Risk | High | Moderate | Open | Training Product Owner
ASSUMPTIONS | Task | Validation/Monitoring | Start Date | End Date | Duration in days | RAID Category | Impact | Probability | Status | Owner
1 | All project stakeholders will adhere to project timelines, processes, and sign-off schedules. | Confirmed through kickoff and governance plan. |  |  |  | Assumption | High | None | Approved | Project Board
2 | Key users and consultants possess the required skills and will receive necessary enablement. | Confirm training plan completion. |  |  |  | Assumption | High | None | Approved | Project Manager
3 | Required IT infrastructure and SAGE servers are stable and secure throughout project. | IT readiness review before Realize phase. |  |  |  | Assumption | High | None | Approved | IT Lead
4 | Political and economic stability in project countries (Nigeria & Kenya). | Monitor external factors through weekly risk review. |  |  |  | Assumption | High | None | Open | Project Manager
5 | All data required for migration will be made available and validated by business. | Continuous follow-up with data owners. |  |  |  | Assumption | High | None | Open | Data Migration Lead
ISSUES | Task | Resolution/Next Step | Start Date | End Date | Duration in days | RAID Category | Impact | Urgency | Status | Owner
1 | Missing or inaccurate master data templates from legacy systems. | Request business sign-off on data templates and mappings. |  |  |  | Issue | High | High | In Progress | Data Team
2 | Lack of clarity in tax and regulatory reporting requirements for local entities. | Engage Finance Product Owner and local compliance officers for validation. |  |  |  | Issue | Moderate | Moderate | In Progress | Finance Product Owner
3 | Limited access to SAGE test environments delaying test execution. | Coordinate with system admin to ensure sandbox availability. |  |  |  | Issue | Moderate | High | In Progress | QA / System Lead
DEPENDENCIES | Task | Mitigation/Action Plan | Start Date | End Date | Duration in days | RAID Category | Impact | Linkage | Status | Owner
1 | Timely delivery of global template and Fit-to-Standard documents from HQ. | Escalate dependency to global PM; include delivery checkpoints. |  |  |  | Dependency | High | None | Open | PM / Solution Architect
2 | Availability of trained key users for UAT and sign-off. | Align UAT plan with business calendar. |  |  |  | Dependency | High | None | Open | QA Manager
3 | Completion of integration setup with third-party systems (POS, Ariba, etc.). | Monitor integration sprint milestones. |  |  |  | Dependency | High | None | Open | Technical Lead
4 | Access to updated SAGE release version for production rollout. | Coordinate with vendor to align system upgrades. |  |  |  | Dependency | Moderate | None | Open | Vendor / PMO

## RISKS
Sage Business Cloud ERP Implementation – RAID Log
RISKS
No. | Task | Mitigation/Action Plan | Start Date | End Date | Duration in days | RAID Category | Impact | Probability | Status | Owner
1 | Limited stakeholder availability during workshops and UAT. | Secure time commitments from functional heads; communicate schedules early; escalate non-attendance. | 2025-11-08 | 2025-12-29 | 52 | Risk | Moderate | High | Resolved | Project Manager
2 | Delay in data migration due to incomplete or poor-quality legacy data. | Alternative connectivity options available (mobile hotspot backup) and backup communication channels established. | 2025-11-08 | 2025-12-29 | 52 | Risk | High | Moderate | Resolved | Data & System Admin Lead
3 | Unstable internet or infrastructure affecting remote sessions and cloud access. | Plan backup connectivity options; coordinate with IT to monitor system health. | 2025-11-08 | 2025-12-29 | 52 | Assumption | Moderate | Moderate | Resolved | IT / Infra Lead
4 | Scope creep due to unapproved local requirements. | Enforce strict change control via PMO; maintain approved backlog. | 2025-11-08 | 2025-12-29 | 52 | Risk | Low | Moderate | Resolved | PMO / Project Manager
5 | Insufficient user adoption post go-live. | Deliver comprehensive training, communication, and post-go-live handholding. | 2025-11-08 | 2025-12-29 | 52 | Risk | Moderate | High | Resolved | Training Product Owner
6 | Change in Governmental Policies: Could affect compliance requirements, budgets, or project approvals. | Monitor regulatory changes; maintain contact with legal/compliance teams. | 2025-11-08 | 2025-12-29 | 52 | Risk | High | Moderate | Resolved | Compliance Manager
7 | System & Infrastructure Availability: Downtime could disrupt operations or delay project timelines. | Implement redundancy and regular system maintenance. | 2025-11-08 | 2025-12-29 | 52 | Risk | High | Moderate | Resolved | IT Manager
8 | Cyber Attack; Data breach, financial loss, or reputational damage. | Strengthen cybersecurity, regular audits, staff training, and backup plans. | 2025-11-08 | 2025-12-29 | 52 | Risk | Very High | Critical | Resolved | IT Security Lead
9 | Staff Turnover: Loss of key skills and project delays. | Develop knowledge transfer plans and staff retention strategies. | 2025-11-08 | 2025-12-29 | 52 | Risk | Low | Moderate | Resolved | HR Manager
10 | Availability (Holidays, Staff Leave): Reduced capacity during critical periods. | Maintain resource planning calendar; ensure backups are assigned. | 2025-11-08 | 2025-12-29 | 52 | Risk | Low | High (seasonal) | Resolved | Project Manager
11 | Unstable internet or infrastructure affecting remote sessions and cloud access. | Alternative connectivity options available (mobile hotspot backup). | 2025-11-08 | 2025-12-29 | 52 | Risk | High |  | Resolved | Project Manager
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## ASSUMPTIONS
Sage Business Cloud ERP Implementation – RAID Log
ASSUMPTIONS
No. | Task | Validation/Monitoring | Start Date | End Date | Duration in days | RAID Category | Impact | Probability | Status | Owner
1 | All project stakeholders will adhere to project timelines, processes, and sign-off schedules. | Confirmed through kickoff and governance plan. | 2025-11-08 | 2025-12-29 | 52 | Assumption | High | None | Approved | Project Board
2 | Key users and consultants possess the required skills and will receive necessary enablement. | Confirm training plan completion. | 2025-11-08 | 2025-12-29 | 52 | Assumption | High | None | Approved | Project Manager
3 | Required IT infrastructure and SAGE servers are stable and secure throughout project. | IT readiness review before Realize phase. | 2025-11-08 | 2025-12-29 | 52 | Assumption | High | None | Approved | IT Lead
4 | Political and economic stability in project countries (Nigeria & Kenya). | Monitor external factors through weekly risk review. | 2025-11-08 | 2025-12-29 | 52 | Assumption | High | None | Resolved | Project Manager
5 | All data required for migration will be made available and validated by business. | Continuous follow-up with data owners. | 2025-11-08 | 2025-12-29 | 52 | Assumption | High | None | Resolved | Data Migration Lead
6 | Availability of key staff and systems throughout the project lifecycle. | Review and confirm availability regularly. | 2025-11-08 | 2025-12-29 | 52 | Assumption | High | None | Resolved | Project Manager
7 | Internet connectivity and cloud platform availability will support project activities as planned. | Review and confirm availability regularly. | 2025-11-08 | 2025-12-29 | 52 | Assumption | High | None | Resolved
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## ISSUES
Sage Business Cloud ERP Implementation – RAID Log
ISSUES
No. | Task | Resolution/Next Step | Start Date | End Date | Duration in days | RAID Category | Impact | Urgency | Status | Owner
1 | Missing or inaccurate master data templates from legacy systems. | Request business sign-off on data templates and mappings. | 2025-11-08 | 2025-12-02 | 52 | Issue | High | High | Resolved | Data Team
2 | Lack of clarity in tax and regulatory reporting requirements for local entities. | Engage Finance Product Owner and local compliance officers for validation. | 2025-11-08 | 2025-12-02 | 52 | Issue | Moderate | Moderate | Resolved | Finance Product Owner
3 | Limited access to SAGE test environments delaying test execution. | Coordinate with system admin to ensure sandbox availability. | 2025-11-08 | 2025-12-02 | 52 | Issue | Moderate | High | Resolved | QA / System Lead
4 | Team member consistently behind schedule | Review workload; provide time management guidance; consider escalation if pattern continues | 2025-08-11 | 2025-12-02 | 52 | Issue | Moderate | Ongoing | Resolved | Project Manager
5 | Compliance Issues: Non-compliance may lead to fines or reputational risk. | Conduct regular compliance checks; update policies as needed. | 2025-11-08 | 2025-12-02 | 52 | Issue | Moderate | High | Resolved | Project Manager
6 | Compressed project timeline may lead to incomplete testing, insufficient user readiness, and reduced stabilization before closure. | "Adjust schedule and notify stakeholders to meet the new closing date." | 2025-11-22 | 2025-12-02 | 52 | Issue | High | High | Resolved | Project Manager
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## DEPENDENCIES
Sage Business Cloud ERP Implementation – RAID Log
DEPENDENCIES
No. | Task | Mitigation/Action Plan | Start Date | End Date | Duration in days | RAID Category | Impact | Linkage | Status | Owner
1 | Timely delivery of global template and Fit-to-Standard documents from HQ. | Escalate dependency to global PM; include delivery checkpoints. | 2025-11-08 | 2025-12-02 | 52 | Dependency | High | None | Resolved | PM / Solution Architect
2 | Availability of trained key users for UAT and sign-off. | Align UAT plan with business calendar. | 2025-11-09 | 2025-12-03 | 52 | Dependency | High | None | Resolved | QA Manager
3 | Completion of integration setup with third-party systems (POS, Ariba, etc.). | Monitor integration sprint milestones. | 2025-11-10 | 2025-12-04 | 52 | Dependency | High | None | Resolved | Technical Lead
4 | Access to updated SAGE release version for production rollout. | Coordinate with vendor to align system upgrades. | 2025-11-11 | 2025-12-05 | 52 | Dependency | Moderate | None | Resolved | Vendor / PMO
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
RAID Category | Impact | Status
Risk | None | Open
Assumption | Low | In Progress
Issue | Moderate | Ongoing
Dependency | High | On-Track
| Critical | Needs Review
Approved
Overdue
On Hold
Resolved
Closed